## Slide 1
PROJECT NAME CHANGE REQUEST |  | Requestor: | 
Reason for change and brief description |  |  | 
Change type | Impact statement |  | 
Scope increase |  |  | 
Scope reduction |  |  | 
Schedule |  |  | 
Cost |  |  | 
Schedule |  |  | 
Milestone | Baseline | Revised | Variance
Cost |  | 
Baseline | Change | Revised

## Slide 2
KITCHEN EXTENSION PROJECT |  | Requestor: | L. Canfield
Reason for change and brief description |  |  | 
When looking at the design we realised that if we extend by an extra 3 feet we will be able to accommodate a washing machine within the planned workspace. This would mean the washing machine could be moved from the garage freeing up much-needed storage space and improving the flow of the house. |  |  | 
Change type | Impact statement |  | 
Scope increase | Additional 3-foot extension to western elevation of plan. Moderate re-design required. |  | 
Scope reduction | n/a |  | 
Schedule | Fully redesigning the space will add an extra week, but it is believed the project end date could be maintained. |  | 
Cost | The redesign will cost approx. £800, whilst the additional materials needed to extend will cost in the region of £2,500. Total cost: £3,300. |  | 
Schedule |  |  | 
Milestone | Baseline | Revised | Variance
Design complete | 6th March | 13th March | 7 days
Cost |  | 
Baseline | Change | Revised
£32,400 | £3,300 | £35,700