## Slide 1: Project Report
Period –
Escalations:
Awareness:
Budget | Spend to date | AFC | Variance
Next 5 Milestones | Baseline | Forecast | Variance | RAG
Risk description | Proposed mitigation | RAG
 | Activity completed. |  | Baseline at risk – awareness/support required.
 | Baseline no longer achievable without escalation. |  | On track to meet baseline.

## Slide 2: Project Report
Period – 14th January – 28th January
Escalations: None at this time.
Awareness: We are forecasting an over-spend, based on fit-out delays. Discussions with contractor to recover the over-run within the plan.
Budget | Spend to date | AFC | Variance
£170,000 | £84,795 | £193,000 | (£13,000)
Next 5 Milestones | Baseline | Forecast | Variance | RAG
Start on site | 23-Nov-21 | 30-Nov-21 | +5 days | 
Site clearance complete (construction-ready) | 28-Feb-22 | 04-Mar-22 | +4 days | 
Infrastructure build complete | 14-Jun-22 | 14-Jun-22 | Nil | 
Fit out complete | 28-Jul-22 | 15-Aug-22 | +13 days | 
Press preview launch | 21-Aug-22 | 21-Aug-22 | Nil | 
Risk description | Proposed mitigation | RAG
There is a risk that the exact marble countertops specified in the design will not be available as the manufacturer has gone out of business. Impact: Delay to procurement/fit-out timescales. Impact to quality requirement. | In discussion with manufacturer to buy remaining stock. Sourcing alternative countertops of similar design/quality. | 
There is a risk that removal of a waste-pipe not shown in the as-built diagrams delays site clearance. Impact: Knock-on delay to construction work starting which may cause ‘Infrastructure build complete’ milestone to be compromised. | A review of the subsequent schedule activities has meant that the four day delay can be accommodated. Closed. | 
 | Activity completed. |  | Baseline at risk – awareness/support required.
 | Baseline no longer achievable without escalation. |  | On track to meet baseline.